## Uttar Pradesh
M o n t h l y P r o g r e s s R e p o r t
Month and Year
Name of the State
Scheme
State | S.No. | Basieline Information for Project sanctioned by CSMC/CSC | [14 empty] | Fund Flow at SLNA |  |  |  | Number of Slums covered In Project | Name of Slums covered In Project | Project Implementation Information on Tenders / Packages |  |  | Schedule |  |  | Receipts from Beneficiaries, SLNA and Expenditure incuured & Utilisation | [6 empty] | Physical Progress in Project | [15 empty] | Remarks if any by
|  | Project Code allotted | City | Project Title | Project Cost | Central Share | Housing Cost | Infrastructure Cost | Sanction of DUs |  |  |  |  | Number of DUs catered in case of Project is having only infrastructure | Status and Date |  | Fund Received from State Government |  | Fund Released to implementing Agency |  |  |  | Estimated cost of all Packages in the Project and so cost of Awarded Packages and their estimated cost |  |  | Actual Start Date of First Package / tender | Schedule Completion of Last Package | Actual Completion Date if Project is completed by Constructing Agencies | Fund Received from SLNA / Beneficiaries / Interest Receipts |  |  | Expenditure incurred in Project |  | Balance Available with ULB in the Bank Account | Utilisation Certificate submitted to SLNA | Number of DUs for construction works taken up or under Progress | Completion of DUs |  |  |  |  | Number of DUs Allotted and Occupied | [6 empty] | Number of Non-Starter DUs due to various reason so far. | Infrastructure
[9 empty] | Construction of DUs - In-SItu | Construction of DUs under Relocation | DUs for Upgrade | Rental DUs | Transit DUs |  | Status -Sanction, Revised , Cancelled | Date | Central Share | Matching State Share | Central Share | Matching State Share |  |  | Sum of Sanction costs of components / items in all the awarded packages Tenders so far | Sum of Awarded Costs of packages / Tenders so far | Sanctioned cost of Components pending for Tendering |  |  |  | ACA received Received from SLNA | State Grant Received from SLNA | Funds collected from Beneficiary | Paid to Project constructing Agencies/ contractors | Fund released to Beneficiaries in case of Beneficiaries led Construction |  |  |  | New Construction in -Situ | New Construction Under Relocation | Rental DUs | Transit DUs | Upgrade | Allotment to SCs | Allotment to STs | Allotment to Minorities | Allotment to OBCs | Allotment to Others | Total DUs Allotted So Far | Total Occupied DUs in all categories |  | Value of work undertaken/ commenced | Value of work Completed so far | SLNA/Implementing Agency (ULB)
[5 empty] | Rs. In Cr. |  |  |  | Nos |  |  |  |  | Nos | Status | Date | Rs. In Cr. |  |  |  | Nos |  | Rs. | Rs. | Rs. | Date | Date | Date | Rs. In Cr. | [6 empty] | Nos | Nos |  |  |  |  | Nos |  |  |  |  | Nos. |  | Nos | Rs. | Rs.
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 21A | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
| H1 | H2 | H3 | H4 | H5 | H6 | H7 | H8 | H9 | H10 | H11 | H12 | H13 | H14 | H15 | H16 | S1 | S2 | S3 | S4 | U1 | U1 A | U2 | U3 | U4 | U5 | U6 | UG A | U7 | U8 | U8 | U9 | U10 | U11 | U12 | U13 | U14 | U15 | U16 | U17 | U18 | U19 | U20 | U21 | U22 | U23 | U24 | U25 | U26 | U27 | U28
Uttar Pradesh | 2: 09150042B1743; 3: Agra; 4: 1536 Dus Bsup For Agra.; Rs. In Cr. 5: 71.3379; Rs. In Cr. 6: 33.0268; Rs. In Cr. 7: 31.258; Rs. In Cr. 8: 40.0799; Date 16: 14/02/2009; Rs. In Cr. 17: 24.7701
Uttar Pradesh | 2: 09150042B1742; 3: Agra; 4: 2335 DUs BSUP for Agra.; Rs. In Cr. 5: 95.1801; Rs. In Cr. 6: 44.0648; Rs. In Cr. 7: 47.1432; Rs. In Cr. 8: 48.0369; Date 16: 13/02/2009; Rs. In Cr. 17: 22.0324
Uttar Pradesh | 2: 09150042B1785; 3: Agra; 4: 2420 Dus Bsup Project At Deori Road In Agra City; Rs. In Cr. 5: 34.777; Rs. In Cr. 6: 16.1005; Rs. In Cr. 7: 29.6869; Rs. In Cr. 8: 5.0901; Date 16: 21/02/2009; Rs. In Cr. 17: 12.0753
Uttar Pradesh | 2: 09150042B1713; 3: Agra; 4: 2708 DUs at Agra Nagar Nigam. Agra UP; Rs. In Cr. 5: 116.248; Rs. In Cr. 6: 53.8185; Rs. In Cr. 7: 54.8213; Rs. In Cr. 8: 61.4267; Date 16: 2009-03-02; Rs. In Cr. 17: 26.9092
Uttar Pradesh | 2: 09150042B1712; 3: Agra; 4: 604 DUs at Gover Chowki. Agra; Rs. In Cr. 5: 35.1433; Rs. In Cr. 6: 16.2701; Rs. In Cr. 7: 12.2016; Rs. In Cr. 8: 22.9417; Date 16: 2009-03-02; Rs. In Cr. 17: 12.2025
Uttar Pradesh | 2: 09150042B1784; 3: Agra; 4: 950 Dus at Agra Nagar Nigam. UP; Rs. In Cr. 5: 39.7763; Rs. In Cr. 6: 18.4149; Rs. In Cr. 7: 19.1674; Rs. In Cr. 8: 20.6089; Date 16: 21/02/2009; Rs. In Cr. 17: 13.8111
Uttar Pradesh | 2: 09150042B1299; 3: Agra; 4: BSUP Scheme for the city of Agra.(Phase0III).Uttar Pradesh; Rs. In Cr. 5: 51.9837; Rs. In Cr. 6: 24.6368; Rs. In Cr. 7: 31.679; Rs. In Cr. 8: 20.3047; Date 16: 30/07/2008; Rs. In Cr. 17: 18.4776
Uttar Pradesh | 2: 09150042B1300; 3: Agra; 4: BSUP Scheme for the city of Agra.(Phase0IV).Uttar Pradesh; Rs. In Cr. 5: 127.2709; Rs. In Cr. 6: 59.4725; Rs. In Cr. 7: 85.9867; Rs. In Cr. 8: 41.2842; Date 16: 30/07/2008; Rs. In Cr. 17: 44.6043
Uttar Pradesh | 2: 09150042B336; 3: Agra; 4: Dpr For Integrated Development Of Kanshi Ram Taj Nagari Phase Ii; Rs. In Cr. 5: 14.7922; Rs. In Cr. 6: 6.7828; Rs. In Cr. 7: 8.7552; Rs. In Cr. 8: 6.037; Date 16: 13/02/2008; Rs. In Cr. 17: 6.7828
Uttar Pradesh | 2: 09150042B337; 3: Agra; 4: Dpr For Integrated Development Of Manniya Shri Kanshi Ram Jee Kalindi Vihar I And Ii; Rs. In Cr. 5: 19.0377; Rs. In Cr. 6: 7.8765; Rs. In Cr. 7: 9.2772; Rs. In Cr. 8: 9.7605; Date 16: 14/03/2008; Rs. In Cr. 17: 7.8766
Uttar Pradesh | 2: 09450101B1740; 3: Allahabad; 4: BSUP Scheme for the construction of 233 DUs in Naini, Allahabad, UP.; Rs. In Cr. 5: 7.3852; Rs. In Cr. 6: 3.4191; Rs. In Cr. 7: 4.6251; Rs. In Cr. 8: 2.7601; Date 16: 14/02/2009; Rs. In Cr. 17: 2.5644
Uttar Pradesh | 2: 09450101B1741; 3: Allahabad; 4: 244 Dus BSUP Scheme for Allahabad.; Rs. In Cr. 5: 15.1403; Rs. In Cr. 6: 7.0094; Rs. In Cr. 7: 4.8383; Rs. In Cr. 8: 10.302; Date 16: 14/02/2009; Rs. In Cr. 17: 5.2572
Uttar Pradesh | 2: 09450101B1703; 3: Allahabad; 4: 411 DUs for Allahabad; Rs. In Cr. 5: 19.1546; Rs. In Cr. 6: 8.8679; Rs. In Cr. 7: 7.1494; Rs. In Cr. 8: 12.0052; Date 16: 2009-03-02; Rs. In Cr. 17: 4.434
Uttar Pradesh | 2: 09450101B1708; 3: Allahabad; 4: 483 DUs with infrastructure facilities at Allahabad City, Dist. Alllahabad, UP.; Rs. In Cr. 5: 23.4391; Rs. In Cr. 6: 10.8514; Rs. In Cr. 7: 9.2674; Rs. In Cr. 8: 14.1717; Date 16: 2009-03-02; Rs. In Cr. 17: 8.1387
Uttar Pradesh | 2: 09450101B352; 3: Allahabad; 4: Integrated Rehabilitation Project Allahabad; Rs. In Cr. 5: 3.3359; Rs. In Cr. 6: 1.5163; Rs. In Cr. 7: 2.64; Rs. In Cr. 8: 0.6959; Date 16: 29/12/2006; Rs. In Cr. 17: 0.37907
Uttar Pradesh | 2: 09342214B1791; 3: Kanpur; 4: 343 Dus for bsup at kanpur in 3 slums; Rs. In Cr. 5: 14.0175; Rs. In Cr. 6: 6.4896; Rs. In Cr. 7: 6.6934; Rs. In Cr. 8: 7.3241; Date 16: 21/02/2009; Rs. In Cr. 17: 6.4896
Uttar Pradesh | 2: 09342214B1701; 3: Kanpur; 4: 416 DUs . Insitu for 2 slums (Bargadiya Purwa & Bara Sirohi); Rs. In Cr. 5: 19.7142; Rs. In Cr. 6: 9.127; Rs. In Cr. 7: 8.0528; Rs. In Cr. 8: 11.6614; Date 16: 2009-03-02; Rs. In Cr. 17: 9.127
Uttar Pradesh | 2: 09342214B1707; 3: Kanpur; 4: 639 DUs at Kanpur in 7 slums; Rs. In Cr. 5: 35.5097; Rs. In Cr. 6: 16.9903; Rs. In Cr. 7: 11.1022; Rs. In Cr. 8: 24.4075; Date 16: 2009-03-02; Rs. In Cr. 17: 16.9903
Uttar Pradesh | 2: 09342214B1790; 3: Kanpur; 4: 704 Dus for BSUP at Kanpur in 6 slums; Rs. In Cr. 5: 29.392; Rs. In Cr. 6: 13.6074; Rs. In Cr. 7: 13.7955; Rs. In Cr. 8: 15.5965; Date 16: 21/02/2009; Rs. In Cr. 17: 13.6074
Uttar Pradesh | 2: 09342214B1865; 3: Kanpur; 4: 726 Dus BSUP Scheme for 3 slums for the town of Kanpur. UP; Rs. In Cr. 5: 30.6633; Rs. In Cr. 6: 14.3959; Rs. In Cr. 7: 14.4067; Rs. In Cr. 8: 16.2566; Date 16: 26/02/2009; Rs. In Cr. 17: 10.797
Uttar Pradesh | 2: 09342214B1789; 3: Kanpur; 4: 753 Dus for Bsup At Kanpur In 3 Slums; Rs. In Cr. 5: 28.5627; Rs. In Cr. 6: 13.2235; Rs. In Cr. 7: 14.4792; Rs. In Cr. 8: 14.0835; Date 16: 21/02/2009; Rs. In Cr. 17: 13.2235
Uttar Pradesh | 2: 09342214B1864; 3: Kanpur; 4: 793 Dus BSUP Scheme for the town of Kanpur. UP; Rs. In Cr. 5: 31.3593; Rs. In Cr. 6: 14.7227; Rs. In Cr. 7: 15.7362; Rs. In Cr. 8: 15.6231; Date 16: 26/02/2009; Rs. In Cr. 17: 14.7227
Uttar Pradesh | 2: 09342214B1787; 3: Kanpur; 4: 816 Dus for BSUP Scheme at Kanpur in 3 slums UP.; Rs. In Cr. 5: 28.5038; Rs. In Cr. 6: 13.1962; Rs. In Cr. 7: 15.8931; Rs. In Cr. 8: 12.6107; Date 16: 21/02/2009; Rs. In Cr. 17: 13.1962
Uttar Pradesh | 2: 09342214B1858; 3: Kanpur; 4: 854 Dus BSUP Scheme for the town of Kanpur for 7 slums. UP; Rs. In Cr. 5: 36.0713; Rs. In Cr. 6: 16.9349; Rs. In Cr. 7: 16.9467; Rs. In Cr. 8: 19.1246; Date 16: 24/02/2009; Rs. In Cr. 17: 16.9349
Uttar Pradesh | 2: 09342214B1874; 3: Kanpur; 4: 871 Dus BSUP Scheme for 4 slums for the town of Kanpur. UP; Rs. In Cr. 5: 36.5107; Rs. In Cr. 6: 17.1411; Rs. In Cr. 7: 17.284; Rs. In Cr. 8: 19.2267; Date 16: 28/02/2009; Rs. In Cr. 17: 12.856
Uttar Pradesh | 2: 09342214B1788; 3: Kanpur; 4: 887 Dus at Kanpur in 7 slums; Rs. In Cr. 5: 36.6763; Rs. In Cr. 6: 16.9798; Rs. In Cr. 7: 17.0032; Rs. In Cr. 8: 19.6731; Date 16: 21/02/2009; Rs. In Cr. 17: 16.9798
Uttar Pradesh | 2: 09342214B536; 3: Kanpur; 4: Detail Project Report of 2950 housing units in 6 slums Kanpur City Phase II; Rs. In Cr. 5: 59.859; Rs. In Cr. 6: 27.2087; Rs. In Cr. 7: 47.2; Rs. In Cr. 8: 12.659; Date 16: 26/09/2007; Rs. In Cr. 17: 6.8022
Uttar Pradesh | 2: 09342214B538; 3: Kanpur; 4: Detail Project Report of 3050 housing units in 6 slums Kanpur City Phase III (KDA); Rs. In Cr. 5: 60.4233; Rs. In Cr. 6: 27.4651; Rs. In Cr. 7: 48.8; Rs. In Cr. 8: 11.6233; Date 16: 26/09/2007; Rs. In Cr. 17: 6.8663
Uttar Pradesh | 2: 09342214B534; 3: Kanpur; 4: Integrated Rehabilitation Project for the Urban Poor Staying in Slums in Kanpur; Rs. In Cr. 5: 8.8527; Rs. In Cr. 6: 4.024; Rs. In Cr. 7: 7.616; Rs. In Cr. 8: 1.2367; Date 16: 2007-02-02; Rs. In Cr. 17: 1.006
Uttar Pradesh | 2: 09272776B1698; 3: Lucknow; 4: 336 DUs for the town of Chak Malhauri. Lucknow. UP; Rs. In Cr. 5: 12.5648; Rs. In Cr. 6: 5.9552; Rs. In Cr. 7: 6.7947; Rs. In Cr. 8: 5.7701; Date 16: 2009-03-02; Rs. In Cr. 17: 5.9552
Uttar Pradesh | 2: 09272776B1711; 3: Lucknow; 4: 487 DUs for Lucknow City.; Rs. In Cr. 5: 26.6236; Rs. In Cr. 6: 12.3258; Rs. In Cr. 7: 9.4914; Rs. In Cr. 8: 17.1322; Date 16: 2009-03-02; Rs. In Cr. 17: 9.2442
Uttar Pradesh | 2: 09272776B1709; 3: Lucknow; 4: 763 DUs with Infrastructure facilities at Lucknow, Distt. Lucknow, UP.; Rs. In Cr. 5: 35.9564; Rs. In Cr. 6: 16.6465; Rs. In Cr. 7: 14.8717; Rs. In Cr. 8: 21.0847; Date 16: 2009-03-02; Rs. In Cr. 17: 12.4848
Uttar Pradesh | 2: 09272776B404; 3: Lucknow; 4: Integrated Rehabilitation Project Lucknow; Rs. In Cr. 5: 32.5265; Rs. In Cr. 6: 14.7847; Rs. In Cr. 7: 25.4592; Rs. In Cr. 8: 7.0673; Date 16: 29/12/2006; Rs. In Cr. 17: 11.0886
Uttar Pradesh | 2: 09272776B3028; 3: Lucknow; 4: Additional Infrastructure component in BSUP Scheme of Lucknow (approved in the 8th CSMC).; Rs. In Cr. 5: 11.6721; Rs. In Cr. 6: 5.4038; Rs. In Cr. 7: 0; Rs. In Cr. 8: 11.6721; Date 16: 2010-05-08; Rs. In Cr. 17: 2.7018
Uttar Pradesh | 2: 09272776B1710; 3: Lucknow; 4: BSUP project for 346 DUs at Lucknow City; Rs. In Cr. 5: 19.3274; Rs. In Cr. 6: 8.9479; Rs. In Cr. 7: 6.7429; Rs. In Cr. 8: 12.5845; Date 16: 2009-03-02; Rs. In Cr. 17: 4.474
Uttar Pradesh | 2: 09272776B406; 3: Lucknow; 4: 8896 Dus BSUP Scheme for Lucknow City, Uttar Pradesh; Rs. In Cr. 5: 177.5272; Rs. In Cr. 6: 82.1886; Rs. In Cr. 7: 144.1152; Rs. In Cr. 8: 33.412; Date 16: 13/09/2007; Rs. In Cr. 17: 61.6413
Uttar Pradesh | 2: 09272776B1699; 3: Lucknow; 4: Under Relocation 1408 DUs at Nai Basti. Lucknow; Rs. In Cr. 5: 49.5703; Rs. In Cr. 6: 23.4931; Rs. In Cr. 7: 28.4729; Rs. In Cr. 8: 21.0974; Date 16: 2009-03-02; Rs. In Cr. 17: 5.8733
Uttar Pradesh | 2: 09272776B1700; 3: Lucknow; 4: Under Relocation. 176 DUs at UMRAO HATA. NISHATGANJ. Lucknow; Rs. In Cr. 5: 5.9513; Rs. In Cr. 6: 2.8205; Rs. In Cr. 7: 3.5591; Rs. In Cr. 8: 2.3922; Date 16: 2009-03-02; Rs. In Cr. 17: 2.8205
Uttar Pradesh | 2: 09143011B1786; 3: Mathura; 4: 2018 Dus BSUP Project at Radhey Shyam Colony. Mathura City; Rs. In Cr. 5: 88.1017; Rs. In Cr. 6: 65.2605; Rs. In Cr. 7: 40.6213; Rs. In Cr. 8: 47.4804; Date 16: 21/02/2009; Rs. In Cr. 17: 48.9453
Uttar Pradesh | 2: 09143011B1873; 3: Mathura; 4: 530 Dus BSUP Scheme for 5 slums at Mathura. UP; Rs. In Cr. 5: 23.4241; Rs. In Cr. 6: 17.3182; Rs. In Cr. 7: 10.885; Rs. In Cr. 8: 12.5391; Date 16: 28/02/2009; Rs. In Cr. 17: 8.659
Uttar Pradesh | 2: 09143011B1872; 3: Mathura; 4: 534 Dus BSUP Scheme for 6 slums at Mathura. UP; Rs. In Cr. 5: 23.6597; Rs. In Cr. 6: 17.5257; Rs. In Cr. 7: 10.9671; Rs. In Cr. 8: 12.6926; Date 16: 28/02/2009; Rs. In Cr. 17: 13.1442
Uttar Pradesh | 2: 09143011B1704; 3: Mathura; 4: 560 DUs for Gopal Nagar. Mathura; Rs. In Cr. 5: 31.6964; Rs. In Cr. 6: 23.4789; Rs. In Cr. 7: 11.8384; Rs. In Cr. 8: 19.858; Date 16: 2009-03-02; Rs. In Cr. 17: 17.6091
Uttar Pradesh | 2: 09143011B1705; 3: Mathura; 4: 608 Dus BSUP Scheme for Laxmi Nagar. Mathura.; Rs. In Cr. 5: 37.6269; Rs. In Cr. 6: 27.8718; Rs. In Cr. 7: 12.8531; Rs. In Cr. 8: 24.7738; Date 16: 2009-03-02; Rs. In Cr. 17: 20.904
Uttar Pradesh | 2: 09143011B1484; 3: Mathura; 4: BSUP Scheme at Jaisinghpura. Mathura. UP; Rs. In Cr. 5: 5.0087; Rs. In Cr. 6: 3.7102; Rs. In Cr. 7: 2.43; Rs. In Cr. 8: 2.5787; Date 16: 16/12/2008; Rs. In Cr. 17: 2.7827
Uttar Pradesh | 2: 09143011B421; 3: Mathura; 4: Integrated Rehabilitation Project Mathura; Rs. In Cr. 5: 4.5779; Rs. In Cr. 6: 3.3294; Rs. In Cr. 7: 3.48; Rs. In Cr. 8: 1.0979; Date 16: 29/12/2006; Rs. In Cr. 17: 3.3294
Uttar Pradesh | 2: 09073035B1855; 3: Meerut; 4: 500 Dus Bsup Scheme Achronda And Kanshi. Meerut. Up; Rs. In Cr. 5: 22.18; Rs. In Cr. 6: 8.9418; Rs. In Cr. 7: 9.4689; Rs. In Cr. 8: 12.7111; Date 16: 24/02/2009; Rs. In Cr. 17: 8.9418
Uttar Pradesh | 2: 09073035B1697; 3: Meerut; 4: 629 DUs for the City of Meerut; Rs. In Cr. 5: 30.9801; Rs. In Cr. 6: 14.823; Rs. In Cr. 7: 11.8252; Rs. In Cr. 8: 19.1549; Date 16: 2009-03-02; Rs. In Cr. 17: 14.823
Uttar Pradesh | 2: 09073035B1856; 3: Meerut; 4: 632 Dus BSUP Scheme for Abdullapur & Karimnagar. Meerut. UP; Rs. In Cr. 5: 27.3185; Rs. In Cr. 6: 11.0138; Rs. In Cr. 7: 11.9687; Rs. In Cr. 8: 15.3498; Date 16: 24/02/2009; Rs. In Cr. 17: 11.0138
Uttar Pradesh | 2: 09073035B1715; 3: Meerut; 4: 677 DUs BSUP Project at Meerut.; Rs. In Cr. 5: 31.6592; Rs. In Cr. 6: 14.9105; Rs. In Cr. 7: 12.7276; Rs. In Cr. 8: 18.9316; Date 16: 2009-03-02; Rs. In Cr. 17: 14.9105
Uttar Pradesh | 2: 09073035B1857; 3: Meerut; 4: 681 Dus BSUP Scheme at Meerut. UP; Rs. In Cr. 5: 30.4459; Rs. In Cr. 6: 14.3613; Rs. In Cr. 7: 14.5235; Rs. In Cr. 8: 15.9224; Date 16: 24/02/2009; Rs. In Cr. 17: 14.3613
Uttar Pradesh | 2: 09073035B1714; 3: Meerut; 4: 694 DUs BSUP project for Meerut City.; Rs. In Cr. 5: 28.8416; Rs. In Cr. 6: 13.7998; Rs. In Cr. 7: 13.0472; Rs. In Cr. 8: 15.7944; Date 16: 2009-03-02; Rs. In Cr. 17: 13.7997
Uttar Pradesh | 2: 09073035B1696; 3: Meerut; 4: 723 DUs for Meerut City; Rs. In Cr. 5: 37.7045; Rs. In Cr. 6: 18.0404; Rs. In Cr. 7: 12.6857; Rs. In Cr. 8: 25.0188; Date 16: 2009-03-02; Rs. In Cr. 17: 18.0404
Uttar Pradesh | 2: 09073035B1716; 3: Meerut; 4: 731 DUs BSUP Project at Meerut.; Rs. In Cr. 5: 34.7093; Rs. In Cr. 6: 15.9842; Rs. In Cr. 7: 13.7428; Rs. In Cr. 8: 20.9665; Date 16: 2009-03-02; Rs. In Cr. 17: 15.9843
Uttar Pradesh | 2: 09073035B1695; 3: Meerut; 4: 768 DUs for the City of Meerut; Rs. In Cr. 5: 33.0845; Rs. In Cr. 6: 15.8299; Rs. In Cr. 7: 13.5885; Rs. In Cr. 8: 19.496; Date 16: 2009-03-02; Rs. In Cr. 17: 15.8299
Uttar Pradesh | 2: 09073035B1301; 3: Meerut; 4: BSUP Scheme for the Urban Poor at Lohiya Nagar, Meerut, Uttar Pradesh; Rs. In Cr. 5: 23.5585; Rs. In Cr. 6: 10.8067; Rs. In Cr. 7: 15.9264; Rs. In Cr. 8: 7.6321; Date 16: 30/07/2008; Rs. In Cr. 17: 10.8067
Uttar Pradesh | 2: 09073035B428; 3: Meerut; 4: BSUP scheme for Meerut Phase II; Rs. In Cr. 5: 18.2516; Rs. In Cr. 6: 8.3723; Rs. In Cr. 7: 12.579; Rs. In Cr. 8: 5.6726; Date 16: 2008-07-03; Rs. In Cr. 17: 8.3723
Uttar Pradesh | 2: 09073035B1702; 3: Meerut; 4: Insitu 655 DUs for the City of Meerut; Rs. In Cr. 5: 29.0119; Rs. In Cr. 6: 13.8813; Rs. In Cr. 7: 12.314; Rs. In Cr. 8: 16.6979; Date 16: 2009-03-02; Rs. In Cr. 17: 13.8813
Uttar Pradesh | 2: 09073035B426; 3: Meerut; 4: Integrated Upgradation and Housing Project for 5 slums Meerut; Rs. In Cr. 5: 32.8357; Rs. In Cr. 6: 14.9253; Rs. In Cr. 7: 18.6; Rs. In Cr. 8: 14.2357; Date 16: 29/12/2006; Rs. In Cr. 17: 14.9253
Uttar Pradesh | 2: 09073035B3808; 3: Meerut; 4: Detailed Project Report for "Implementation of BSUP project for the construction of 225 Dus with Infrastructure facilities at Kidwai Nagar Dist. Meerut. (UP)".; Rs. In Cr. 5: 11.2802; Rs. In Cr. 6: 4.7976; Rs. In Cr. 7: 6.5205; Rs. In Cr. 8: 4.7597; Date 16: 30/05/2011; Rs. In Cr. 17: 1.1994
Uttar Pradesh | 2: 09675005B1867; 3: Varanasi; 4: 1068 Dus BSUP Scheme at Varanasi city. UP; Rs. In Cr. 5: 43.3558; Rs. In Cr. 6: 20.0722; Rs. In Cr. 7: 21.3295; Rs. In Cr. 8: 22.0263; Date 16: 26/02/2009; Rs. In Cr. 17: 10.036
Uttar Pradesh | 2: 09675005B1719; 3: Varanasi; 4: 1305 Dus Bsup Project For The City Of Varanasi.; Rs. In Cr. 5: 56.7426; Rs. In Cr. 6: 26.2697; Rs. In Cr. 7: 25.4535; Rs. In Cr. 8: 31.2891; Date 16: 2009-03-02; Rs. In Cr. 17: 19.7021
Uttar Pradesh | 2: 09675005B1706; 3: Varanasi; 4: 585 DUs for Varanasi.; Rs. In Cr. 5: 24.8078; Rs. In Cr. 6: 11.4851; Rs. In Cr. 7: 10.1748; Rs. In Cr. 8: 14.633; Date 16: 2009-03-02; Rs. In Cr. 17: 8.6139
Uttar Pradesh | 2: 09675005B1717; 3: Varanasi; 4: 728 DUs BSUP project for Varanasi.; Rs. In Cr. 5: 34.3166; Rs. In Cr. 6: 15.8873; Rs. In Cr. 7: 14.2237; Rs. In Cr. 8: 20.0929; Date 16: 2009-03-02; Rs. In Cr. 17: 7.9436
Uttar Pradesh | 2: 09675005B1866; 3: Varanasi; 4: 768 Dus BSUP scheme at Varanasi City. UP; Rs. In Cr. 5: 32.2573; Rs. In Cr. 6: 14.9339; Rs. In Cr. 7: 15.2137; Rs. In Cr. 8: 17.0436; Date 16: 26/02/2009; Rs. In Cr. 17: 7.467
Uttar Pradesh | 2: 09675005B1718; 3: Varanasi; 4: 776 DUs BSUP Project for the Varanasi City.; Rs. In Cr. 5: 30.5873; Rs. In Cr. 6: 14.1608; Rs. In Cr. 7: 15.1613; Rs. In Cr. 8: 15.426; Date 16: 2009-03-02; Rs. In Cr. 17: 10.6206
Uttar Pradesh | 2: 09675005B1451; 3: Varanasi; 4: BSUP Scheme for Jaiprakash Nagar slum in the city of Varanasi. Distt. Varanasi. UP; Rs. In Cr. 5: 5.1064; Rs. In Cr. 6: 2.3639; Rs. In Cr. 7: 2.3469; Rs. In Cr. 8: 2.7595; Date 16: 2008-10-12; Rs. In Cr. 17: 1.773
Uttar Pradesh | 2: 09675005B1450; 3: Varanasi; 4: BSUP Scheme for Mahespur slum in the city of Varanasi. Distt. Varanasi. UP; Rs. In Cr. 5: 4.6836; Rs. In Cr. 6: 2.1682; Rs. In Cr. 7: 2.1556; Rs. In Cr. 8: 2.528; Date 16: 2008-10-12; Rs. In Cr. 17: 1.6263
Uttar Pradesh | 2: 09675005B1449; 3: Varanasi; 4: BSUP Scheme for Rupanpur slum in the city of varanasi. Distt. Varanasi. UP; Rs. In Cr. 5: 8.4509; Rs. In Cr. 6: 3.9122; Rs. In Cr. 7: 4.1894; Rs. In Cr. 8: 4.2615; Date 16: 2008-10-12; Rs. In Cr. 17: 2.9343
Uttar Pradesh | 2: 09675005B601; 3: Varanasi; 4: DPR for Integrated Development of Newada NAT BASTi including Insitu development and relocation Varansi; Rs. In Cr. 5: 5.6922; Rs. In Cr. 6: 2.6043; Rs. In Cr. 7: 3.0087; Rs. In Cr. 8: 2.6835; Date 16: 27/02/2008; Rs. In Cr. 17: 1.3022
Total | Rs. In Cr. 5: 2353.795; Rs. In Cr. 6: 1149.0408; Rs. In Cr. 7: 1238.8628; Rs. In Cr. 8: 1114.9322; Nos 9: 0; Nos 10: 0; Nos 11: 0; Rs. In Cr. 17: 850.48; Nos 35: 0; Nos 37: 0; Nos 40: 0; Nos. 46: 0; Nos 48: 0